Action Plan on Sustainable Development Goal( SDG )s for the Administrative Reforms & Training and Personnel Departments

In order to achieve effective integration of the entire governmental machinery, rejuvenation of the system is required – a key to achieve the SDGs of different departments. Proper management of human resources is essential for positive transformation of the present system to an all pervasive     “ People Partnership Project ” approach. Assessment, evaluation , analysis and monitoring of the prevailing system to identify the  gap and then to bridge it is to be pursued as a continuous process.

To reach the SDGs, capacity of the government functionaries are to be enhanced to the maximum extent possible. As is envisaged in the vision for Assam in 2030, first 2 to 3 years will have to be devoted to put the system into place which will act as a harbinger of change. What is required is a critical and dispassionate self examination for zeroing in  on the deficits on the system and then start a synergic up gradation for optimum utilization of the human resource and transform it into the agent of change.

For motivation and team work, leadership quality of the government functionaries will have to be built up. The Administrative Reforms & Training and Personnel Departments will have to reinvent the prevailing system to walk in tandem with the ever changing social dynamics and evolving technological disruptions.

It is possible only through regular and consistent review and evaluation of the functioning of the system time and again because change is the only constant variable in our fast changing world. Use of ICT and sharing of knowledge with experienced hands will have to be used as the effective means for ways forward in days ahead.

Efforts of the Departments will be to strengthen the system by equipping it with an able and dynamic work force and an effective mechanism to face the challenges of time and making it live up to the expectation of the public, to help in building up trust between citizens and the government- to make them two side of the same coin.

Work Study

|  | Baseline 2016-17 | Target 2017-18 | Target 2018-19 | Target 2019-2020 |
| --- | --- | --- | --- | --- |
| Identification of areas | 60% | 100% |  |  |
| Strategy mapping |  | 25% | 100% |  |
| Revamping |  |  | 70% | 100% |

Tuning of Service Rules

|  | Baseline 2016-17 | Target 2017-18 | Target 2018-19 | Target 2019-20 |
| --- | --- | --- | --- | --- |
| Identification of issues |  |  | 100% |  |
| Resolving of the issues |  |  | 100% |  |

Capacity Building

|  | Baseline 2016-17 | Target 2017-18 | Target 2018-19 | Target 2019-20 |
| --- | --- | --- | --- | --- |
| Identification of training needs | 10% | 100% |  |  |
| Design and module |  | 50% | 100% |  |
| Training |  |  | 30% | 100% |

Institution Development

|  | Baseline 2016-17 | Target 2017-18 | Target 2018-19 | Target 2019-20 |
| --- | --- | --- | --- | --- |
| Concept Paper & DPR | 100% |  |  |  |
| A A |  | 100% |  |  |
| Implementation |  | 20% | 50% | 100% |

Institutional Reforms

|  | Baseline 2016-17 | Target 2017-18 | Target 2018-19 | Target 2019-21 |
| --- | --- | --- | --- | --- |
| Identification of Needs | 100% |  |  |  |
| Strategy mapping |  | 100% |  |  |
| Short term targets |  |  | 100% |  |
| Long term targets |  |  |  | 100% |
| ACCSDP* | 5% | 25% | 50% | 100% |

*Assam Citizen Centric Service Delivery Project- an EAP funded by the World Bank for electronic service delivery system of identified(55 till date) services of 18 departments (till date).

To start with, a Work Study will have to be made by a competent organization  to assess the functioning of the departments to identify the issues related to the capacity of the available human resource, division of work, delegation of power team building chemistry etc. And then an all out concerted effort will have to be made  for the required revamping. Our time line :

| November,2016 | Submission of Budget Estimate |
| --- | --- |
| April-May , 2017 | Budget Allocation |
| 31st May , 2017 | Floating of RFQ |
| 20th August, 2017 | Issue of work order |
| February, 2018 | Work Study to be completed |
| 31st March, 2018 | Scrutiny of the Work Study Report |
| 15th April, 2018 | Departments to be intimated about the findings of the Work Study Report. |
| 15th May,2018 | Review of the Departments’ response to the findings of the Work Study Report |
| 30th June, 2018 | Rationalization of works |
| 28th December, 2018 | 1st Review on impact |
| 31st January, 2019 | Finalization of the response of Administrative Reforms & Training and Personnel Departments. |
| 15th February, 2019 | Sharing , briefing and debriefing with departments |
| 30th August, 2019 | 2nd Review |
| 29th November, 2019 | Re visioning of the Action Plan |

Tuning of Service Rules: Once the revamping of the prevailing system is given effect, changes and  amendments of the existing service rules will be required as a corollary. The Departments’ time line to cope with this issue is as follows:

| 31st May,2018 | Discussion with all departments. |
| --- | --- |
| 30th June , 2018 | Receiving proposals from departments for amendments |
| 28th December,2018 | Vetting completed |
| 15th January, 2019 | Reviewing on Department’s ATR on amendment of service rules |

Capacity building will have to be taken as a major thrust area for which we will first have to find out the areas where focus will have to be concentrated. Initially, all needs will have to be found out. Timeline of our approach is as follows:

| 31st April, 2017 | Receiving nomination for ToTs of all departments for TNA/organizational analysis for the respective departments. |
| --- | --- |
| 31st October,2017 | Completion of the training of all ToTs. |
| October, 2017 | Submission of Budget Estimate by the departments. |
| November-December,2017 | Departments will complete TNA |
| 28th February,2018 | Design of training for the needs identified |
| April, 2018 | Budget Allocation |
| 30th April,2018 | Training Modules for all training needs to be prepared |
| 15th June, 2018 | Publication of Training calendar |
| September 2018 onward | Training starts as per calendar |

Institution Development is another requirement which is to be addressed with a vision for decades to come. To cater to the needs of future years , the Administrative Reforms & Training Department has come with an action plan to translate hon’ble Chief Minister’s dream into reality-building a top class training institute at Umrangsu :

| 15th November,2016 | Concept Paper to be prepared |
| --- | --- |
| 30th November,2016 | Submission of Budget Estimate |
| 15th February,2017 | Preparation of tentative DPR |
| 31st March, 2017 | Firmed up DPR |
| 30th April,2017 | Govt. approval |
| April , 2017 | Budget Allocation |
| 30th September,2017 | Administrative Approval |
| October, 2017 | Submission of Budget Estimate |
| 15th November, 2017 | RFQ to be floated by PW Department |
| 30th December,2017 | Work starts. |
| April, 2018 | Budget Allocation |
| July, 2018 | Review of work on site |
| October,2018 | Submission of Budget Estimate |
| November, 2018 | Review of work on site |
| February, 2019 | Review of work on site |
| April ,2019 | Budget Allocation |
| July , 2019, | Review of work on site |
| October, 2019 | Review of work on site |
| October,2019 | Submission of Budget Estimate |
| January, 2019 | Review of work on site |
| March, 2020 | Review of work on site |

Institutional Reforms is the core area where drastic steps are to be taken to transform the State Public Service Commission into an institution through which the best and only the best is recruited. Reports of Tapan Lal Baruah Committee, MP Bezbarua Committee and RT Jindal Committee had been published on the web for public view and suggestions. To strengthen the institution of Public Service Commission and to ensure a transparent recruitment process, no stone will be left unturned. Our  timeline is:

| 31st March,2017 | Determination of the expected performance to be completed |
| --- | --- |
| 31st July,2017 | Assessing the gap |
| August to October 2017 | Action on solution to be decided and taken by the Govt. |
| October, 2017 | Budget estimate as required will be submitted |
| 31st March, 2018 | Strategies shall be put in place |
| April, 2018 | Budget Allocation |
| 31st August , 2018 | Action begins |
| 31st March , 2019 | Short term targets to be achieved |
| 30th April 2019 | Long term targets to be achieved |
| July 2019 | 1st Impact Review |
| August 2019 | Action to be taken as decided on Impact Review. |
| January 2020 | 2nd Impact Review |

Another area where reform is to brought in the process of submission of ACRs by ACS officers which is yet to be made online .It is realized to be a necessity to facilitate a seamless flow from submission to acceptance. Our timeline to switch over to the online mode is :

| 30th August,2017 | Aadhaar Registration of ACS officers |
| --- | --- |
| 29th October,2017 | Guidelines for online submission of ACR |
| 30th December,2017 | Review of functioning of the system |
| 30th January,2018 | Action to be taken as decided on the Review |
| January,2019 | Review |

ACCSDP-  PMU has been set up with Rs 2.52 Crore already received. Negotiation with the World Bank by year end,2016.

DRAFT

Justification for proposing schemes under the signatuire projects for 2017-2018 under the Administrative Reforms and Training Department

- Training Academy at Umrangshu is an institution to cater to the needs of State's Civil Servants and officers of the State and the neighbouring states which is a requirement to be addressed with a vision for decades to come. To cater to the needs of future years, the Administrative Reforms & Training Department has come with an action plan to translate hon’ble Chief Minister’s dream into reality-building a top class training institute at Umrangsu.

Amount proposed for 2017-2018 = Rs. 200.00 Lakh for topography survey and preliminary 	expenditure.

- Efficiency is the oft spoken word in the parlence of the bureaucracy and the Administration. With the change of socio-economic background and changes in technology the methods of doing particular jobs have changed over the years and more changes are going to come. The Work process is also going to be changed accordingly. This will also require advance preparation regarding manpower planning. This necessitates that a Work Study will have to be made by a competent organization  to assess the functioning of the departments to identify the issues related to the capacity of the available human resource, division of work, delegation of power, team building capacity etc. and then an all out concerted effort will have to be made for the required revamping. Rationalization of works vis-a-vis available human resource for humanly possible out put of work in all Governmant Departments to reach respective SDGs by 2030 is a requisite to bridge the gap wherever analysed, keeping in view the likely changes in technology platform, This may be a new idea not known to have been done in other states.

An RFQ prepared by the DoT, AASC has already been forwarded to the Finance and P & D 	Department for their views, suggestions and concurrence.

Amount proposed for 2017-2018 = Rs. 100.00 Lakh

- Grade-III and Grade-IV support staff of the Departments are the skeleton of office structure who need orientation and refresher courses from time to time. With changing time the support staff are to be kept abreast of the requirement of capacity expected from them and help them to live up to the mark. There has not been any concerted effort to address this issue till now. By empowering them with exposure to the changing needs a positive change in creating a vibrant ambience in all work place can be achieved. To decentralize training and capacity building of the support staff in a continuous manner, a permanent facility is required at District level. To start with, four places out of the following six have been proposed for this purpose :

Guwahati, Dibrugarh/Majuli, Silchar/Badarpur, Bongaigaon

Amount proposed for 2017-2018 = Rs. 2000.00 Lakh (@Rs. 500.00 Lakh per Institute)

- Reforms in APSC is being taken up to restore Public faith in the entire system of recruitment to various Government posts through the Commission. Discussion with the commission have been made in this regard and it is felt that it is essential to revamp the examination system in the line of the UPSC. For this new technology platform will have to be used by the Commission by optimising uses of disruptive technology in various stages of the selection process so that only the best is recruited for Government jobs.

Amount proposed for 2017-2018 = Rs. 100.00 Lakh

Other additional requirement :

- Financial assistance to candidates clearing UPSC (Prelims) Examination have been given from the Relief Fund of the Hon'ble Chief Minister till this year. CMO has asked this to be taken up by the A.R. & T Department from 2017-2018. Therefore, an amount of Rs. 100.00 Lakh will be required under proper Head of Account in addition to the normal establishment cost of the AASC.

Action Plan on Sustainable Development Goal( SDG )s for the Administrative Reforms & Training and Personnel Departments

In order to achieve effective integration of the entire governmental machinery, rejuvenation of the system is required. Proper management of human resources is essential for positive transformation of the present system. Capacity of the government functionaries are to be enhanced to the maximum extent possible. As is envisaged in the vision for Assam in 2030, first 2 to 3 years will have to be devoted to put the system into place which will act as a harbinger of change.  Professionalism is to be brought to all rank and file to ensure optimum utilization of the human resource and transform it into the agent of change. Without a thoroughly trained and motivated support staff professionalism in service delivery to the citizens will be very difficult to infuse.

There has not been any concerted effort to address this issue till now. By empowering the support staff with exposure to the changing needs a positive change in creating a vibrant ambience in all work place can be achieved. To decentralize training and capacity building of the support staff in a continuous manner, a permanent facility is required at District level.

For motivation and team work, leadership quality of the government functionaries will have to be built up. At present, the AASC as the only training institute in the state is too far stretched to cater to this need covering all employees of all the departments in the state. It is essential to have its satellite training centres at the districts to effectively address this serious issue. To start with, Training centres at four districts viz. Majuli, Guwahati, Bongaigaon and Silchar are  a necessity to cover Grade III and IV employees in all the districts.

This will help all the Grade III and IV employees to get exposure to the objective of various Govt programmes and schemes, relevant guidelines and their expected role in meeting up the expectation of the citizens in the process of  service delivery mechanism.